## Sheet1
| Task Name | Ideation Date | Subtasks | Status Date | Status | Comments
1 | Python Tutorial/Course | 2019-06-18
|  | 2019-06-19 | Find topics, read documents |  | Ongoing
|  |  | Topic 1: How to structure python code and styleguidelines | 2019-06-19 | Done | https://docs.python-guide.org/writing/structure/
[5 empty] | Ongoing | style guide for python code: https://www.python.org/dev/peps/pep-0008/
[5 empty] | ToDo | doc strings: https://www.python.org/dev/peps/pep-0257/
[5 empty] | ToDo | https://realpython.com/python-pep8/#why-we-need-pep-8
|  |  |  | 2019-06-19 | Done | https://realpython.com/python-modules-packages/
|  |  |  | 2019-06-19 | Done | https://realpython.com/python-application-layouts/
|  | 2019-06-19 | Topic 2: Baisc Python syntax and functionality |  | ToDo
Languge Reference https://docs.python.org/3/reference/index.html#reference-index
Standard Library reference https://docs.python.org/3/library/
|  | 2019-06-20 | Topic 3: NumPy tutorial
2 | Matplotlib Tutorial/Course | 2019-06-18 |  |  | ToDo
|  | 2019-06-19 | Find One
3 | TestCases for the RigidBody Class | 2019-06-18 |  | 2019-06-20 | Done
4 | Add info and configuration on the noise level parameters | 2019-06-18 |  | 2019-06-19 | Done | Comments were created to explain the Random Walk process, coefficients and reasoning. For now however the noise component was removed from RBD, noise to be included in the dynamic model (forces and torques).
5 | Create Quad model/class for forces and torques | 2019-06-19 |  |  | Ongoing | almost done, consider adding a motor FOS step response, and to add configurable noise
6 | Enlarge the utils library with Rotation - Euler Angles transformation to be able to do plotting in the test cases | 2019-06-19 |  | 2019-06-19 | Done
7 | Improve the logger , and write to files | 2019-06-19 |  |  | Done | enough for this time, open new issue again if needed
8 | Add quaternions function and compare results with rotation matrix | 2019-06-19 |  | 2019-06-20 | Done | to investigate more numerically stable formulas, see if I can do better in tests
9 | find a tool to extarct documentation from the docstrings to test it works ok | 2019-06-20 |  | 2019-06-20 | Done | use python help() function, as described here https://wiki.python.org/moin/DocumentationTools
| read all again about first order systems | 2019-06-21 |  |  | ToDo