## Code
| Task Name | Ideation Date | CAT | Status Date | Status | Comments
3 | TestCases for the RigidBody Class | 2019-06-18 | TESTS | 2019-06-20 | Done
4 | Add info and configuration on the noise level parameters | 2019-06-18 |  | 2019-06-19 | Done | Comments were created to explain the Random Walk process, coefficients and reasoning. For now however the noise component was removed from RBD, noise to be included in the dynamic model (forces and torques).
5 | Create Quad model for forces and torques | 2019-06-19 | DEV | 2019-06-21 | Done | consider adding some dynamic response for the motors later when you find some docs for it
6 | Unit Tests for the quadftau | 2019-06-22 | TESTS | 2019-06-22 | Done
6 | Enlarge the utils library with Rotation - Euler Angles transformation to be able to do plotting in the test cases | 2019-06-19 | DEV | 2019-06-19 | Done
7 | Improve the logger , and write to files | 2019-06-19 | DEV MISC |  | Done | enough for this time, open new issue again if needed
8 | Add quaternions function and compare results with rotation matrix | 2019-06-19 | DEV | 2019-06-20 | Done | to investigate more numerically stable formulas, see if I can do better in tests
9 | find a tool to extarct documentation from the docstrings to test it works ok | 2019-06-20 | DEV MISC | 2019-06-20 | Done | use python help() function, as described here https://wiki.python.org/moin/DocumentationTools
10 | to add x configuration (only have + now) | 2019-06-22 | DEV |  | ToDo
11 | to add wind to the whole setup | 2019-06-22 | DEV |  | ToDo
12 | Component testing rigidbody plus qftau | 2019-06-22 | TESTS | 2019-06-23 | Done

## Reading
|  |  | Done | https://docs.python-guide.org/writing/structure/
|  |  | Ongoing | style guide for python code: https://www.python.org/dev/peps/pep-0008/
|  |  | ToDo | doc strings: https://www.python.org/dev/peps/pep-0257/
|  |  | ToDo | https://realpython.com/python-pep8/#why-we-need-pep-8
|  |  | Done | https://realpython.com/python-modules-packages/
|  |  | Done | https://realpython.com/python-application-layouts/
Languge Reference https://docs.python.org/3/reference/index.html#reference-index
Standard Library reference https://docs.python.org/3/library/
r | read all again about first order systems | 2019-06-21 | Done | made a file but did not commit, I am not using it anywhere in the project