## Main Code
Idx | Task Name | Ideation Date | CAT | Closing Date | Status | Comments
1 | TestCases for the RigidBody Class | 2019-06-18 | TESTS | 2019-06-20 | Done
2 | Add info and configuration on the noise level parameters | 2019-06-18 |  | 2019-06-19 | Done | Comments were created to explain the Random Walk process, coefficients and reasoning. For now however the noise component was removed from RBD, noise to be included in the dynamic model (forces and torques).
3 | Create Quad model for forces and torques | 2019-06-19 | DEV | 2019-06-21 | Done | consider adding some dynamic response for the motors later when you find some docs for it
4 | Unit Tests for the quadftau | 2019-06-22 | TESTS | 2019-06-22 | Done
5 | Enlarge the utils library with Rotation - Euler Angles transformation to be able to do plotting in the test cases | 2019-06-19 | DEV | 2019-06-19 | Done
6 | Improve the logger , and write to files | 2019-06-19 | DEV MISC |  | Done | enough for this time, open new issue again if needed
7 | Add quaternions function and compare results with rotation matrix | 2019-06-19 | DEV | 2019-06-20 | Done | to investigate more numerically stable formulas, see if I can do better in tests
8 | find a tool to extarct documentation from the docstrings to test it works ok | 2019-06-20 | DEV MISC | 2019-06-20 | Done | use python help() function, as described here https://wiki.python.org/moin/DocumentationTools
9 | to add x configuration (only have + now) | 2019-06-22 | DEV |  | ToDo
10 | to add wind to the whole setup | 2019-06-22 | DEV |  | ToDo
11 | Component testing rigidbody plus qftau | 2019-06-22 | TESTS | 2019-06-23 | Done
12 | BUG: Propeller reaction torque/ torque effect is opposite the blades rotation | 2019-06-25 | BUG |  | ToDo
13 | BUG: negative inertia tensor matrix !! | 2019-06-26 | BUG | 2019-06-26 | Done

## Visualization Code
Idx | Task Name | Ideation Date | CAT | Closing Date | Status | Comments
1 | First tests with Panda3D | 2019-06-24 |  | 2019-06-24 | Done | Installed Panda3D in Anaconda. Modified the panda example receive keys, and move the bear around. I also tested changing the HPR of the main actor
2 | Attach camera to follow actor | 2019-06-24 |  |  | ToDo | Should be easy since now I have code setting the camera position
3 | Explore envir and actor file formats | 2019-06-24 |  |  | ToDo | https://www.panda3d.org/manual/?title=Models_and_Actors

## Reading
|  |  | Done | https://docs.python-guide.org/writing/structure/
|  |  | Ongoing | style guide for python code: https://www.python.org/dev/peps/pep-0008/
|  |  | ToDo | doc strings: https://www.python.org/dev/peps/pep-0257/
|  |  | ToDo | https://realpython.com/python-pep8/#why-we-need-pep-8
|  |  | Done | https://realpython.com/python-modules-packages/
|  |  | Done | https://realpython.com/python-application-layouts/
Languge Reference https://docs.python.org/3/reference/index.html#reference-index
Standard Library reference https://docs.python.org/3/library/
r | read all again about first order systems | 2019-06-21 | Done | made a file but did not commit, I am not using it anywhere in the project

## Course Materials
|  | Ideation | Category | Closing date | Status
1 | Bundle startup (slide templete, tools, folder structure) | 2019-06-23 |  | 2019-06-23 | Done
2 | L001 Course introduction Slides | 2019-06-23 |  | 2019-06-23 | Done
3 | L001 Course introduction Video | 2019-06-23 |  | 2019-06-26 | Done
4 | L002+L003 Slides and transcript | 2019-06-24 |  | 2019-06-26 | Done
5 | L004 Rigid Body Dynamics Slides | 2019-06-24 |  |  | Ongoing
6 | L004 Rigid Body Dynamics Slides - ang vel 2D proof | 2019-06-28 |  |  | Postponed
7 | L001+L002+L003 video, with noise red, udemy upload |  |  | 2019-06-29 | Finished
8 | L004 Rigid Body Dynamics Transscript | 2019-06-29 |  |  | Ongoing