## Main Code
Idx | Task Name | Ideation Date | CAT | Closing Date | Status | Comments
1 | TestCases for the RigidBody Class | 2019-06-18 | TESTS | 2019-06-20 | Done
2 | Add info and configuration on the noise level parameters | 2019-06-18 |  | 2019-06-19 | Done | Comments were created to explain the Random Walk process, coefficients and reasoning. For now however the noise component was removed from RBD, noise to be included in the dynamic model (forces and torques).
3 | Create Quad model for forces and torques | 2019-06-19 | DEV | 2019-06-21 | Done | consider adding some dynamic response for the motors later when you find some docs for it
4 | Unit Tests for the quadftau | 2019-06-22 | TESTS | 2019-06-22 | Done
5 | Enlarge the utils library with Rotation - Euler Angles transformation to be able to do plotting in the test cases | 2019-06-19 | DEV | 2019-06-19 | Done
6 | Improve the logger , and write to files | 2019-06-19 | DEV MISC |  | Done | enough for this time, open new issue again if needed
7 | Add quaternions function and compare results with rotation matrix | 2019-06-19 | DEV | 2019-06-20 | Done | to investigate more numerically stable formulas, see if I can do better in tests
8 | find a tool to extarct documentation from the docstrings to test it works ok | 2019-06-20 | DEV MISC | 2019-06-20 | Done | use python help() function, as described here https://wiki.python.org/moin/DocumentationTools
9 | to add x configuration (only have + now) | 2019-06-22 | DEV | 2019-07-06 | Done
10 | to add wind to the whole setup | 2019-06-22 | DEV |  | Postponed
11 | Component testing rigidbody plus qftau | 2019-06-22 | TESTS | 2019-06-23 | Done
12 | BUG: Propeller reaction torque/ torque effect is opposite the blades rotation | 2019-06-25 | BUG |  | Done
13 | BUG: negative inertia tensor matrix !! | 2019-06-26 | BUG | 2019-06-26 | Done
14 | IMPROVEMENT: the rotm with diag elements with -1/2 , and multiplication by 2 just once. should be faster | 2019-07-01 |  | 2019-07-06 | Done | Not much faster. Why is q slower than rotm ? And less precise in the short run. But rotm we get weird determinant over time.
15 | Investsigate implementation of Runge kutta ( at least RK4 ) | 2019-07-06 |  |  | Postponed
16 | Investigate better step responses for both cross and plus configuration | 2019-07-08 |  |  | ToDo
17 Lie group integration techniques for quaternions |  | 2019-07-08 |  |  | ToDo

## Visualization Code
Idx | Task Name | Ideation Date | CAT | Closing Date | Status | Comments
1 | First tests with Panda3D | 2019-06-24 |  | 2019-06-24 | Done | Installed Panda3D in Anaconda. Modified the panda example receive keys, and move the bear around. I also tested changing the HPR of the main actor
2 | Attach camera to follow actor | 2019-06-24 |  | 2019-07-06 | Done | Should be easy since now I have code setting the camera position +camera.lookAt(object) function
3 | Explore envir and actor file formats | 2019-06-24 |  |  | ToDo | https://www.panda3d.org/manual/?title=Models_and_Actors
4 | Quadrotor model |  |  | 2019-07-06 | Done | Manged with two Blender addons, one to read Google SketchuP format, and one to export to egg format. And found a *.skp file for the Crazyflie.
5 | Textures for the quadrotor | 2019-07-06 |  | 2019-07-07 | Ongoing
6 | Motion/Actor for the quadrotor | 2019-07-06 |  |  | ToDo
7

## Reading
Idx | Task Name | Ideation Date | CAT | Closing Date | Status | Comments
[5 empty] | Done | https://docs.python-guide.org/writing/structure/
[5 empty] | Ongoing | style guide for python code: https://www.python.org/dev/peps/pep-0008/
[5 empty] | ToDo | doc strings: https://www.python.org/dev/peps/pep-0257/
[5 empty] | ToDo | https://realpython.com/python-pep8/#why-we-need-pep-8
[5 empty] | Done | https://realpython.com/python-modules-packages/
[5 empty] | Done | https://realpython.com/python-application-layouts/
Languge Reference https://docs.python.org/3/reference/index.html#reference-index
Standard Library reference https://docs.python.org/3/library/
| read all again about first order systems | 2019-06-21 |  |  | Done | made a file but did not commit, I am not using it anywhere in the project
| INS alignment | 2019-07-06 |  |  | ToDo | Investigate topic accelerometer not placed exactly at the center of mass - MEMS board alignment

## Course Materials
|  | Ideation | Category | Closing date | Status
1 | Bundle startup (slide templete, tools, folder structure) | 2019-06-23 |  | 2019-06-23 | Done
2 | L001 Course introduction Slides | 2019-06-23 |  | 2019-06-23 | Done
3 | L001 Course introduction Video | 2019-06-23 |  | 2019-06-26 | Done
4 | L002+L003 Slides and transcript | 2019-06-24 |  | 2019-06-26 | Done
5 | L004 Rigid Body Dynamics Slides | 2019-06-24 |  | 2019-07-02 | Done
6 | L004 Rigid Body Dynamics Slides - ang vel 2D proof | 2019-06-28 |  |  | Postponed
7 | L001+L002+L003 video, with noise red, udemy upload |  |  | 2019-06-29 | Done
8 | L004 Rigid Body Dynamics Transscript | 2019-06-29 |  | 2019-07-02 | Done
9 | Use equation numbering in the slides and refer to equations in the transcript for lessons 4 and 5 | 2019-06-29 |  |  | Done
10 | L005 Rigid Body Dynamics Slides + Transscript | 2019-06-29 |  | 2019-06-29 | Done
11 | Record video for lecture 004 | 2019-06-29 |  | 2019-07-02 | Done
12 | Record video for lecture 005 | 2019-07-02 |  | 2019-07-03 | Done
13 | Lecture L006 slides | 2019-06-29 |  | 2019-07-05 | Done
14 | video correct Lecture 3, 5 and Lecture 6 | 2019-07-06 |  | 2019-07-08 | Done
15 | Lecture 007 video | 2019-07-07 |  | 2019-07-08 | Done
16 | Lecture 008 slides & video | 2019-07-07 |  |  | ToDo